## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | SM/10806 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 1316/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 0.52 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | SM/10806 | New | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 2057/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 0.52 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Chisopani under Kurseong Sub Division ,PHED,GTA | SM/10806 | New | SURFACE WATER BASED LOWER CHISOPANI PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000083/2022-2023 | 606/NKWSMD | 26/05/2022 | 11/12/2024 | NARESH RAI | 69.92 | 62.3 | 89.09 | 100
Total | [13 empty] | 70.97 | 62.3 | 87.78