## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | SM/10807 | New | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 1317/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 0.52 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | SM/10807 | New | Material Requisition To Resource Division |  |  | RTOR000138/2022-2023 | 1258/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 0.52 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Laptcher (Rohini) under Kurseong Sub Division ,PHED,GTA | SM/10807 | New | SURFACE WATER BASED LAPCHER (ROHINI) PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000082/2022-2023 | 603/NKWSMD | 26/05/2022 | 25/07/2022 | HARI PRASAD CHETTRI | 63.44 | 0 | 0 | 100
Total | [13 empty] | 64.48 | 0 | 0