## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10808 | New | Material Requisition To Resource Division |  |  | RTOR000139/2022-2023 | 1259/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 1.47 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10808 | New | SURFACE WATER BASED TINDHARIA TEA ESTATE PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000081/2022-2023 | 604/NKWSMD | 26/05/2022 | 21/01/2023 | KARUNAMAYA ENTERPRISES | 108.97 | 81.83 | 75.09 | 80
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Tindharia Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10808 | New | ADDITIONAL WORK FOR TINDHARIA TEA ESTATE WATER SUPPLY SCHEME UNDER BLOCK-KURSEONG DISTRICT-DARJEELING, KURSEONG DIVISION PHED |  |  | ORD/000011/2025-2026 | 497/NKWSMD | 09/04/2025 | 06/10/2025 | SUNIT DEEP RAI | 65.5 | 0 | 0 | 0
Total | [13 empty] | 175.93 | 81.83 | 46.51