## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10809 | New | SURFACE WATER BASED JOGMAYA TEA ESTATE PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E.D-GTA |  |  | ORD/000285/2022-2023 | 2083/NKWSMD | 10/01/2023 | 09/07/2023 | MS CHAMLING CONSTRUCTION | 66.72 | 27.2 | 40.77 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Jogmaya Tea Estate under Kurseong Sub Division ,PHED,GTA | SM/10809 | New | Material Requisition To Resource Division |  |  | RTOR000224/2022-2023 | 2602/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.89 | 0 | 0 | 0
Total | [13 empty] | 67.61 | 27.2 | 40.24