## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Creating gravity based Provision Of Drinking water from spring water source for 79 numbers of school under Kurseong Sub-Division in the District of Darjeeling Under Neorakhola water Suppply Division ,Kalimpong PHE Dte TSM No. 009890 |  | Junior Engineer IV | ORD/000023/2022-2023 | 255/NKWSMD | 06/05/2022 | 02/11/2022 | GARGO TRADERS | 211.58 | 99.22 | 46.89 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Hiring of vehicle for the office of Superintending Engineer, G.T.A-Circle, P.H. Engineering Directorate for the period of 6(Six) months, other than GTA Area. Note: With effect from date of issuing work order. |  |  | ORD/000376/2022-2023 | 2230/NKWSMD | 31/01/2023 | 30/07/2023 | SUJIT DEB | 0.99 | 2.33 | 235.17 | 25
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | CREATING GRAVITY BASED PROVISION OF DRINKING WATER FROM SPRING WATER SOURCE FOR 93 NOS OF SCHOOL, 23 NOS OF ICDS CENTRES, 11 NOS OF HEALTH CENTRES, 8 NOS OF GRAM PANCHAYAT IN UNDER RANGLI RANGLIOT BLOCK IN THE DISTRICT OF DARJEELING UNDER NEORAKHOLA WATER SUPPLY DIVISION ,KALIMPONG PHE DTE. TSM No. 009891 | Assistant Engineer I | Junior Engineer I | ORD/000022/2022-2023 | 254/NKWSMD | 06/05/2022 | 02/11/2022 | GARGO TRADERS | 320.59 | 76.07 | 23.73 | 100
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area. Note: With effect from the date of issuing work order. |  |  | ORD/000243/2023-2024 | 860/NKWSMD | 31/07/2023 | 27/01/2024 | SUJIT DEB | 0.99 | 0 | 0 | 50
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | (Continuation) Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months, other than G.T.A Area from 01/02/2024 to 31/07/2024. Note: With effect from the date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000292/2023-2024 | 170/NKWSMD | 31/01/2024 | 29/07/2024 | SUJIT DEB | 0.99 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Hiring of Vehicle for the Office of the Superintending Engineer, G.T.A-Circle, Public Health Engineering Directorate for the period of 6 (Six) Months for G.T.A Area. Note: With effect from the date of issuing work order. |  |  | ORD/000242/2023-2024 | 859/NKWSMD | 31/07/2023 | 31/01/2024 | YAMA CONSTRUCTIONS LLP | 0.99 | 0 | 0 | 100
7 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Additional works in various Schools in connection with creating gravity based provision of drinking water from spring water source for 21 number of schools under Kurseong Sub Division in the District of Darjeeling under Neorakhola Water Supply and Maintenance Division Public Health Engineering Directorate. | Assistant Engineer I | Junior Engineer III | ORD/000406/2022-2023 | 1178/NKWSMD | 18/08/2022 | 17/09/2022 | GARGO TRADERS | 4.84 | 0 | 0 | 100
8 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of March. |  |  | BILL/00176/2024-2025 | BP-2024-25-170 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.17 | 0 | 0 | 0
9 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of August. |  |  | BILL/00177/2024-2025 | BP-2024-25-163 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.11 | 0 | 0 | 0
10 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of October. |  |  | BILL/00179/2024-2025 | BP-2024-25-165 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.12 | 0 | 0 | 0
11 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of January. |  |  | BILL/00182/2024-2025 | BP-2024-25-168 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.12 | 0 | 0 | 0
12 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of September. |  |  | BILL/00178/2024-2025 | BP-2024-25-164 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.14 | 0 | 0 | 0
13 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of February. |  |  | BILL/00175/2024-2025 | BP-2024-25-169 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.18 | 0 | 0 | 0
14 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of December. |  |  | BILL/00181/2024-2025 | BP-2024-25-167 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.17 | 0 | 0 | 0
15 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision of Drinking water from spring water source of school (79 nos) under Kurseong Sub-Division, in the District of Darjeeling under Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate Kalimpong | SM/10814 | School | Placement of 1 Nos of site inspection vehicle at the disposal of the undersigned for the Period of 10 Days, as and when required basis for the month of November. |  |  | BILL/00180/2024-2025 | "BP-2024-25-166 | 01/08/2024 | 01/08/2024 | PAWAN TAMANG | 0.15 | 0 | 0 | 0
Total | [13 empty] | 542.13 | 177.61 | 32.76