## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik,Naxalbari | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. | SM/10815 | New | Material Requisition To Resource Division |  |  | RTOR000161/2022-2023 | 2375/NKWSMD | 03/02/2023 | 03/02/2023 | Resource Division | 9.18 | 0 | 0 | 0
2 | DARJEELING | Mirik,Naxalbari | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. | SM/10815 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00489/2023-2024 | BP-2023-24-296 | 02/11/2023 | 02/11/2023 | WBSEDCL | 4.87 | 0 | 0 | 0
3 | DARJEELING | Mirik,Naxalbari | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. | SM/10815 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00488/2023-2024 | BP-2023-24-295 | 02/11/2023 | 02/11/2023 | WBSEDCL | 6.14 | 0 | 0 | 0
4 | DARJEELING | Mirik,Naxalbari | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. | SM/10815 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. |  |  | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 04/12/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
5 | DARJEELING | Mirik,Naxalbari | Neorakhola W/S & Mtc.Div. | Nipania Piped water Supply Scheme. | SM/10815 | New | Implementation Of ODEX Tube Well based 02(Two) number of pipe water supply Scheme having provision of 2(Two) number of RCC OHR viz 300 Cum & 200Cum and other related works for 6(Six) villages in GTA Area. |  |  | ORD/000094/2022-2023 | 825/NKWSMD | 30/06/2022 | 16/12/2024 | M/S KAMAK ENGINEERS AND CO. | 783.01 | 0 | 0 | 100
Total | [13 empty] | 1013.55 | 0 | 0