## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. |  |  | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 07/09/2026 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 88.33 | 12.44 | 100
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Material Requisition To Resource Division |  |  | RTOR000155/2022-2023 | 2373/NKWSMD | 03/02/2023 | 03/02/2023 | Resource Division | 4.21 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00492/2023-2024 | BP-2023-24-291 | 02/11/2023 | 02/11/2023 | WBSEDCL | 0.36 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00493/2023-2024 | BP-2023-24-292 | 02/11/2023 | 02/11/2023 | WBSEDCL | 0.46 | 0 | 0 | 0
5 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | ADDITIONAL BALANCE WORK ITEMS IN VARIOUS ONGOING PIPED WATER SUPPLY SCHEMES (NIPANIA, BARA CHENGA, PANTHABARI, GARIDHURA & SIMULBARI) UNDER KURSEONG DIVISION, PHED-GTA. |  |  | ORD/000130/2024-2025 | 2228/NKWSMD | 09/12/2024 | 04/12/2025 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 210.35 | 0 | 0 | 10
6 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 1781/NKWSMD | 23/09/2024 | 23/09/2024 | Resource Division | 0.54 | 0 | 0 | 0
7 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | payment for wbsedcl |  |  | BILL/00706/2023-2024 | BP-2023-24-475 | 28/01/2024 | 28/01/2024 | WBSEDCL | 4.15 | 0 | 0 | 0
8 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Garidhora (M.Bari) Tea Garden Area Piped Water Supply Scheme | SM/10818 | New | payment for wbsedcl |  |  | BILL/00707/2023-2024 | BP-2023-24-476 | 28/01/2024 | 28/01/2024 | WBSEDCL | 5.49 | 0 | 0 | 0
Total | [13 empty] | 935.76 | 88.33 | 9.44