## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | SM/10819 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00173/2023-2024 | BP-2023-24-128 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | SM/10819 | New | Quotation of wbsedcl for electrical service connection |  |  | BILL/00172/2023-2024 | BP-2023-24-127 | 27/07/2023 | 27/07/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | SM/10819 | New | Quotation of WBSEDCL for electrical service connection |  |  | BILL/00494/2023-2024 | BP-2023-24-290 | 02/11/2023 | 02/11/2023 | WBSEDCL | 0.09 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Mini Piped Water supply Scheme for Champasari Forest Village ,Chhota Adalpur ,Paharu Village under Block Kurseong Dist Darjeeling | SM/10819 | New | Implementation of ODEX tube well based 02(two) numbers of pipe water supply scheme having provision of 2(two) numbers of RCC OHR viz 150 cum & 150 cum and other related works for 6(six) villages in GTA area. |  |  | ORD/000095/2022-2023 | 826/NKWSMD | 30/06/2022 | 07/09/2026 | ANUGRAH CONSTRUCTION PRIVATE LIMITED | 710.19 | 95 | 13.38 | 100
Total | [13 empty] | 710.46 | 95 | 13.37