## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | SM/10825 | New | Surface Water Based Upper Mamring Piped Water Supply Scheme to accmmodate FHTC in Kurseong Block within Darjeeling District under Kurseong Sub-Division, P.H.E.D-G.T.A |  |  | ORD/000145/2022-2023 | 836/NKWSMD | 30/06/2022 | 28/09/2022 | AJAY RAI | 89.52 | 35.7 | 39.88 | 85
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | SM/10825 | New | Material Requisition To Resource Division |  |  | RTOR000141/2022-2023 | 2061/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 0.94 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Mamring under Kurseong Sub Division ,PHED,GTA | SM/10825 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00448/2023-2024 | BP-2023-24-289 | 01/11/2023 | 01/11/2023 | DIVISIONAL FOREST OFFICER | 49.25 | 0 | 0 | 0
Total | [13 empty] | 139.72 | 35.7 | 25.55