## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA | SM/10826 | New | Material Requisition To Resource Division |  |  | RTOR000267/2022-2023 | 2839/NKWSMD | 17/03/2023 | 17/03/2023 | Resource Division | 1.03 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Middle Mamring under Kurseong Sub Division ,PHED,GTA | SM/10826 | New | SURFACE WATER BASED MIDDLE MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT, UNDER KURSEONG DIVISION, P.H.E-GTA. |  |  | ORD/000223/2022-2023 | 1121/NKWSMD | 05/08/2022 | 29/09/2025 | PREM CHANDRA RAI | 96.87 | 51.27 | 52.93 | 100
Total | [13 empty] | 97.9 | 51.27 | 52.37