## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA | SM/10827 | New | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 2060/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 1.21 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Lower Mamring under Kurseong Sub Division ,PHED,GTA | SM/10827 | New | SURFACE WATER BASED LOWER MAMRING PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, PHE DTE. |  |  | ORD/000090/2022-2023 | 609/NKWSMD | 26/05/2022 | 29/12/2024 | NAVRATNA CONSTRUCTION CO | 125.37 | 31.19 | 24.88 | 80
Total | [13 empty] | 126.58 | 31.19 | 24.64