## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | SM/10829 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 59/NKWSMD | 24/04/2023 | 24/04/2023 | Resource Division | 0.5 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | SM/10829 | New | ADDITIONAL WORK FOR SURFACE WATER BASED TOROYOK KHASMAHAL PIPED WATER SUPPLY SCHEME TO ACCOMMODATE FUNCTIONAL HOUSEHOLD TAP CONNECTION ((FHTC) IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT. |  |  | ORD/000049/2025-2026 | 638/NKWSMD | 05/05/2025 | 03/08/2025 | SURAJMULL PRABHUDAYAL | 22.11 | 0 | 0 | 100
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | SM/10829 | New | PWS scheme for Upper Toroyuk(SM/10829) |  |  | BILL/00675/2024-2025 | BP-2024-25-480 | 17/03/2025 | 17/03/2025 | DIVISIONAL FOREST OFFICER | 2.99 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | PWSS Scheme for Upper Toroyuk under Kurseong Sub Division ,PHED,GTA | SM/10829 | New | SURFACE WATER BASED UPPER TOROYUK PWSS TO ACCMMODATE FHTC IN KURSEONG BLOCK WITHIN DARJEELING DISTRICT UNDER KURSEONG DIVISION, P.H.E-GTA. |  |  | ORD/000222/2022-2023 | 1120/NKWSMD | 05/08/2022 | 20/07/2025 | BIKRAM RAI | 102.03 | 21.54 | 21.12 | 100
Total | [13 empty] | 127.63 | 21.54 | 16.88