## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Thulung Gaon | SM/10830 | New | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 1321/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 0.66 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Thulung Gaon | SM/10830 | New | PIPED WATER SUPPLY SCHEME FOR THULUNG GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000088/2022-2023 | 612/NKWSMD | 26/05/2022 | 25/07/2022 | SEWARO CONSTRUCTION COMPANY | 75.88 | 55.29 | 72.87 | 95
Total | [13 empty] | 76.53 | 55.29 | 72.24