## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singbuli factory gaon | SM/10831 | New | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 1322/NKWSMD | 09/09/2022 |  | Resource Division | 1.3 | 0 | 0 | 0
2 | DARJEELING | Mirik | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singbuli factory gaon | SM/10831 | New | PIPED WATER SUPPLY SCHEME FOR SINGBULLI FACTORY GAON UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000089/2022-2023 | 611/NKWSMD | 26/05/2022 | 25/07/2022 | M/S JAI BHAWANI CONSTRUCTION CO | 63.19 | 7.34 | 11.61 | 97
Total | [13 empty] | 64.49 | 7.34 | 11.38