## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 | New | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 1884/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 0.52 | 0 | 0 | 0
2 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 | New | PIPED WATER SUPPLY SCHEME FOR POKHRIABONG BUSTY NO. 5 UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000107/2022-2023 | 628/NKWSMD | 26/05/2022 | 25/07/2022 | HARI PRASAD CHETTRI | 85.92 | 0 | 0 | 100
3 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 | New | Material Requisition To Resource Division |  |  | RTOR000166/2022-2023 | 2571/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.52 | 0 | 0 | 0
4 | DARJEELING | Jorebunglow Sukiapokhri | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Pokhriabong Busty 5 No. | SM/10832 | New | Material Requisition To Resource Division |  |  | RTOR000085/2022-2023 | 1367/NKWSMD | 21/09/2022 | 21/09/2022 | Resource Division | 0.52 | 0 | 0 | 0
Total | [13 empty] | 87.49 | 0 | 0