## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 1882/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 1.9 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 | New | Piped Water Supply Scheme for Jhepi & Gurdung under Jal Jeevan Mission and Jal Swapno Programme. |  |  | ORD/000138/2022-2023 | 818/NKWSMD | 30/06/2022 | 25/02/2023 | VINAYAK CONSTRUCTION | 303.13 | 0 | 0 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 | New | Material Requisition To Resource Division |  |  | RTOR000165/2022-2023 | 2570/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.9 | 0 | 0 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme For Jhepi & Gurdung. | SM/10833 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 1365/NKWSMD | 21/09/2022 | 21/09/2022 | Resource Division | 1.9 | 0 | 0 | 0
Total | [13 empty] | 308.84 | 0 | 0