## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | (Continuation) Engagement of 01 (one) no. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Superintending Engineer, GTA, P.H.E. Dte from 01.06.2023 to 31.07.2023. | Assistant Engineer II | Junior Engineer I | ORD/000069/2023-2024 | 378/NKWSMD | 31/05/2023 | 30/07/2023 | THE ELECTRIC SPHERE | 0.39 | 0.39 | 100 | 100
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | (Continuation) Engagement of 02 (Two) nos. computer operator (Graduate with Certificate in computer Application) for the works related to JJM/Jal Swapno at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2023 to 31.07.2023. | Assistant Engineer II | Junior Engineer I | ORD/000068/2023-2024 | 377/NKWSMD | 31/05/2023 | 30/07/2023 | THE ELECTRIC SPHERE | 0.79 | 0.79 | 100 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | Engagement of 2 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/09/2023. |  | Junior Engineer I | ORD/000205/2023-2024 | 848/NKWSMD | 28/07/2023 | 26/09/2023 | THE ELECTRIC SPHERE | 0.93 | 0.79 | 84.83 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 1271/NKWSMD | 05/09/2022 |  | Resource Division | 0.66 | 0 | 0 | 0
5 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | PIPED WATER SUPPLY SCHEME FOR KOLBONG UNDER JAL SWAPNO PROGRAMME. (BLOCK-DARJEELING-PULBAZAR) |  |  | ORD/000091/2022-2023 | 610/NKWSMD | 26/05/2022 | 22/11/2022 | HEMRAJ NIROLA | 80.89 | 70.09 | 86.65 | 0
6 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | Engagement of 1(One) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the S.E. GTA, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer II | Junior Engineer I | ORD/000152/2022-2023 | 681/NKWSMD | 31/05/2022 | 31/05/2023 | THE ELECTRIC SPHERE | 2.47 | 1.97 | 79.48 | 45
7 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | Engagement of 2(Two) no. computer operator (graduate with certificate in computer application) for the works related to JJM/Jal swapna at the Office of the Executive Engineer, Neorakhola W/S & Mtc. Division, P.H.E. Dte from 01.06.2022 to 31.05.2023 | Assistant Engineer II | Junior Engineer I | ORD/000150/2022-2023 | 680/NKWSMD | 31/05/2022 | 12/06/2022 | THE ELECTRIC SPHERE | 4.98 | 1.57 | 31.6 | 95
8 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Kolbong | SM/10834 | New | Engagement of 1 (One) number Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission/ Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply and Maintenance Division, Public Health Engineering Directorate from 01/08/2023 to 30/11/2023 | Assistant Engineer II | Junior Engineer I | ORD/000207/2023-2024 | 851/NKWSMD | 28/07/2023 | 25/11/2023 | THE ELECTRIC SPHERE | 0.87 | 0.39 | 45.21 | 90
Total | [13 empty] | 91.98 | 75.99 | 82.62