## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. | SM/10836 | New | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 1881/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 0.52 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. | SM/10836 | New | Material Requisition To Resource Division |  |  | RTOR000164/2022-2023 | 2569/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.52 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. | SM/10836 | New | PIPED WATER SUPPLY SCHEME FOR DARAGOAN LEKHARGA UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME. |  |  | ORD/000086/2022-2023 | 613/NKWSMD | 26/05/2022 | 25/07/2022 | SUNIL SHARMA | 58.05 | 0 | 0 | 100
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Daragoan Lekharga. | SM/10836 | New | ADDITIONAL WORK FOR PIPED WATER SUPPLY SCHEME FOR DARAGOAN UNDER PULL BIJANBARI BLOCK DARJEELING DIVISION PHED TO ACCOMODATE FHTC IN PULL BIJANBARI BLOCK |  |  | ORD/000077/2025-2026 | 967/NKWSMD | 03/07/2025 | 01/09/2025 | SUNIL SHARMA | 6.93 | 0 | 0 | 0
Total | [13 empty] | 66.02 | 0 | 0