## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | SM/10837 | New | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 1257/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 0.98 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | SM/10837 | New | PIPED WATER SUPPLY SCHEME FOR 4th DIVISION: PHUBTSHERING TEA GARDEN UNDER JAL SWAPNO PROGRAMME. |  |  | ORD/000087/2022-2023 | 614/NKWSMD | 26/05/2022 | 17/08/2024 | KAMAKHYA ENTERPRISES | 92.66 | 0 | 0 | 100
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for No-4 Division , Phubtshering Tea Garden | SM/10837 | New | WBSEDCL4003424527 |  |  | BILL/00643/2024-2025 | BP-2024-25-447 | 28/11/2024 | 28/11/2024 | WBSEDCL | 0 | 0 | 0 | 0
Total | [13 empty] | 93.64 | 0 | 0