## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. | SM/11300 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 1313/NKWSMD | 09/09/2022 |  | Resource Division | 0.34 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection for PWS scheme at Chandraman Goan. | SM/11300 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for Piped Water Supply Scheme at Chandraman Gaon Gram Panchyat Paila Goan S D- 2 Block- Mirik TSM No. 009302 |  |  | ORD/000125/2022-2023 | 805/NKWSMD | 30/06/2022 | 29/08/2022 | MS. SURYA I PVT. LTD COMPANY | 18.95 | 0 | 0 | 98
Total | [13 empty] | 19.29 | 0 | 0