## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail | SM/11305 | Retrofitting | Continuation Hiring of vehicle for the office of Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for the period of 6 (Six) months. Note: With effect from date of issuing work order. | Assistant Engineer II | Junior Engineer I | ORD/000248/2023-2024 | 1141/NKWSMD | 29/09/2023 | 29/03/2024 | S S CONSTRUCTIONS | 0.99 | 2.13 | 214.87 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme Dara Goan Khoprail | SM/11305 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation for work for PWS Scheme for Dara Goan, Khoprail: Gram Panchyat -Soureni-II, Block Mirik TSM No. 009308 |  |  | ORD/000015/2022-2023 | 783/NKWSMD | 30/06/2022 | 29/08/2022 | RAMESH PRADHAN AND CO. | 12.59 | 11.93 | 94.73 | 100
Total | [13 empty] | 13.58 | 14.05 | 103.49