## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under JSP Programme for PWS Scheme for Chota Tingling | SM/11309 | Retrofitting | Providing Functional household tap connection under Jal Swapno Programme including augmentation work for PWS Scheme for Chotta Tingling: Gram Panchyat- Soureni-II , Block Mirik TSM No. 009480 |  |  | ORD/000017/2022-2023 | 787/NKWSMD | 30/06/2022 | 29/08/2022 | MAHENDRA ADHIKARI | 7.72 | 7.44 | 96.29 | 100
Total | [13 empty] | 7.72 | 7.44 | 96.29