## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. | SM/11320 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 1295/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 1.44 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty ( Lower kharaya and upper Kharaya Busty habitaion ) under Kurseong Sub-Division PHED, GTA. | SM/11320 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Kharey Busty (Lower kharaya and upper Kharaya Busty habitaion) under Kurseong Sub-Division PHED, GTA. |  |  | ORD/000118/2022-2023 | 799/NKWSMD | 30/06/2022 | 29/08/2022 | SAI ENTERPRISE | 16.5 | 0 | 0 | 100
Total | [13 empty] | 17.94 | 0 | 0