## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis | SM/11322 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 1297/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 1.07 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden ( Khundrukey busty,lower chimney,majuwa busty,mohan majuwa,titney busty habitaion ) under Kurseong Sub-Divis | SM/11322 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Majuwa Tea Garden (Khundrukey Busty, Lower Chimney, Majuwa Busty, Mohan Majuwa, Titney Busty habitation) under Kurseong Sub-Division P.H.E.D GTA. |  |  | ORD/000114/2022-2023 | 794/NKWSMD | 30/06/2022 | 14/02/2025 | MS JAGANNATH PRASAD | 11.97 | 0 | 0 | 55
Total | [13 empty] | 13.04 | 0 | 0