## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div | SM/11323 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 1298/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 1.66 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation ) under Kurseong Sub-Div | SM/11323 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Sepoydhura Tea Garden (Bhutia Busty,Aringalay Gairi Gaon,Gairi Gaon and Sepoy Dhura Bajar habitation) under Kurseong Sub-Division PHED, GTA. |  |  | ORD/000122/2022-2023 | 802/NKWSMD | 30/06/2022 | 29/08/2022 | PHURBA RUMBA | 20.05 | 18.75 | 93.52 | 100
Total | [13 empty] | 21.71 | 18.75 | 86.36