## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | SM/11324 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 1299/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 2.61 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. | SM/11324 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Rohini Tea garden (Lapchay Kheti,Rohini chisoo pani habitation) under Kurseong Sub-Division PHED, GTA. |  |  | ORD/000116/2022-2023 | 796/NKWSMD | 30/06/2022 | 29/08/2022 | PREM KUMAR PRADHAN | 27.69 | 26.69 | 96.41 | 100
Total | [13 empty] | 30.3 | 26.69 | 88.1