## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA | SM/11331 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 1305/NKWSMD | 09/09/2022 |  | Resource Division | 1.91 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Ghoomli Tea Estate under Kurseong-Sub Division, PHED, GTA | SM/11331 | Retrofitting | Providing Functional household Tap Connection under JJM & JSP Programme including Retrofitting work for PWS scheme for Ghoomti T.E. Mahanadi GP Block Kurseong |  |  | ORD/000131/2022-2023 | 811/NKWSMD | 30/06/2022 | 29/08/2022 | MS CHAMLING CONSTRUCTION | 26.4 | 10.06 | 38.12 | 0
Total | [13 empty] | 28.31 | 10.06 | 35.55