## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA | SM/11332 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 1306/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 1.5 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong-Sub Division, PHED, GTA | SM/11332 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme for Jangpana under Kurseong Sub-Division P.H.E.D GTA. |  |  | ORD/000146/2022-2023 | 837/KWSMD | 30/06/2022 | 29/08/2022 | MS JAGANNATH PRASAD | 23.75 | 0 | 0 | 100
Total | [13 empty] | 25.25 | 0 | 0