## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singtam Tea Garden | SM/11338 | New | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 767/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 2.82 | 0 | 0 | 0
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Piped water supply scheme for Singtam Tea Garden | SM/11338 | New | PIPED WATER SUPPLY SCHEME FOR SINGTAM TEA GARDEN UNDER JAL SWAPNO PROGRAMME. BLOCK: PULBAZAR, DISTRICT: DARJEELING. |  |  | ORD/000088/2023-2024 | 687/NKWSMD | 12/07/2023 | 08/01/2024 | NIMA SHERPA | 173.26 | 0 | 0 | 75
Total | [13 empty] | 176.08 | 0 | 0