## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. | SM/11339 | New | PIPED WATER SUPPLY SCHEME FROM SINGLA TEA GARDEN UNDER DARJEELING DIVISION, PUBLIC HEALTH ENGINEERING DIRECTORATE, G.T.A |  |  | ORD/000226/2022-2023 | 1289/NKWSMD | 08/09/2022 | 30/05/2025 | VINAYAK CONSTRUCTION | 280.33 | 239.96 | 85.6 | 100
2 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. | SM/11339 | New | Material Requisition To Resource Division |  |  | RTOR000109/2022-2023 | 1886/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 4.6 | 0 | 0 | 0
3 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. | SM/11339 | New | Material Requisition To Resource Division |  |  | RTOR000168/2022-2023 | 2605/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 4.6 | 0 | 0 | 0
4 | DARJEELING | Darjeeling Pulbazar | Neorakhola W/S & Mtc.Div. | Singla Tea Garden water supply scheme. | SM/11339 | New | ADDITIONAL WORK FOR SINGLA PIPED WATER SUPPLY SCHEME UNDER BLOCK-JOREBUNGLOW SUKHIAPOKRI DISTRICT-DARJEELING. |  |  | ORD/000009/2025-2026 | 495/NKWSMD | 09/04/2025 | 06/10/2025 | DAJUBHAI CONSTRUCTION | 88.19 | 0 | 0 | 0
Total | [13 empty] | 377.71 | 239.96 | 63.53