## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11344 | New | PWS Scheme at Aringalae with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. |  |  | ORD/000179/2022-2023 | 955/NKWSMD | 12/07/2022 | 09/09/2024 | LAL BAHADUR THAPA | 27.77 | 13.02 | 46.9 | 75
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11344 | New | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1319/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 0.74 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11344 | New | Material Requisition To Resource Division |  |  | RTOR000146/2022-2023 | 2066/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 0.74 | 0 | 0 | 0
4 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Aringalee with Functional Household Tap Connection under Jal Jeevan Mission Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11344 | New | forest clearance of JJM schemes under kurseong Division PHED GTA. |  |  | BILL/00683/2023-2024 | BP-2023-24-445 | 20/01/2024 | 20/01/2024 | DIVISIONAL FOREST OFFICER | 11.16 | 0 | 0 | 0
Total | [13 empty] | 40.4 | 13.02 | 32.23