## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11348 | New | Material Requisition To Resource Division |  |  | RTOR000265/2022-2023 | 2813/NKWSMD | 14/03/2023 |  | Resource Division | 0.46 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Lower Sirubari with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11348 | New | PIPED WATER SUPPLY SCHEME AT LOWER SIRUBARI WITH FUNCTIONAL HOUSEHOLD TAP CONNECTION UNDER JAL JEEVAN MISSION AND JAL SWAPNO PROGRAMME UNDER KURSEONG DIVISION PHED-GTA, DARJEELING. |  |  | ORD/000269/2022-2023 | 1748/NKWSMD | 25/11/2022 | 24/01/2023 | BITIS PRADHAN AND BROTHERS | 24.69 | 2.5 | 10.12 | 100
Total | [13 empty] | 25.15 | 2.5 | 9.94