## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11350 | New | PWS Scheme at Pokhari Tar with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. |  |  | ORD/000181/2022-2023 | 957/NKWSMD | 12/07/2022 | 10/09/2022 | PHURBA RUMBA | 25.37 | 25.18 | 99.28 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11350 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 1320/NKWSMD | 09/09/2022 | 09/09/2022 | Resource Division | 0.22 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Pokhari Tar with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division, PHED, GTA, Darjeeling. | SM/11350 | New | Material Requisition To Resource Division |  |  | RTOR000147/2022-2023 | 2067/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 0.22 | 0 | 0 | 0
Total | [13 empty] | 25.8 | 25.18 | 97.63