## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11351 | New | Material Requisition To Resource Division |  |  | RTOR000149/2022-2023 | 2069/NKWSMD | 05/01/2023 |  | Resource Division | 0.22 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11351 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 530/NKWSMD | 13/06/2023 |  | Resource Division | 2.05 | 0 | 0 | 0
3 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at 3 Nos Montiviote T.E with Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme under Kurseong Sub Division ,PHED,GTA, Darjeeling. | SM/11351 | New | PWS Scheme at 3 Nos Montiviote TE with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. |  |  | ORD/000211/2022-2023 | 984/NKWSMD | 12/07/2022 | 10/09/2022 | PRASANT NIROLA | 17.52 | 6.98 | 39.84 | 0
Total | [13 empty] | 19.78 | 6.98 | 35.29