## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. | SM/11353 | New | Material Requisition To Resource Division |  |  | RTOR000145/2022-2023 | 2065/NKWSMD | 05/01/2023 | 05/01/2023 | Resource Division | 1.23 | 0 | 0 | 0
2 | DARJEELING | Kurseong | Neorakhola W/S & Mtc.Div. | Piped Water Supply Scheme at Sittong III Naspatti Gaon with Functional Household Tap Connection under Jal Jeevan Mission under Kurseong Sub Division PHED GTA Darjeeling. | SM/11353 | New | PWS Scheme at Sittong - III Naspatti Gaon with Functional Household tap connection under Jal Jeevan Mission & Jal Swapno Programme under Kurseong Division PHED, GTA, Darjeeling. |  |  | ORD/000177/2022-2023 | 953/NKWSMD | 12/07/2022 | 09/03/2023 | MS. SURYA I PVT. LTD COMPANY | 62.8 | 32.21 | 51.28 | 82
Total | [13 empty] | 64.04 | 32.21 | 50.3