## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 101 Nos of Aganwadi under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, kalimpong PHE Directorate | SM/11360 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 101 Numbers of Anganwadi Centre under Jorebungalow-Sukhiapokhri Block in the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, Kalimpong P.H.Engineering Directorate. | Assistant Engineer II | Junior Engineer IV | ORD/000148/2022-2023 | 928/NKWSMD | 12/07/2022 | 09/03/2023 | HARI PRASAD CHETTRI | 310.44 | 202.42 | 65.2 | 0
Total | [13 empty] | 310.44 | 202.42 | 65.2