## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Aganwadi Centers in Block- Mirik, under the District of Darjeeling ,under Neorakhola water Suppply Division ,Kalimpong PHE Dte,. | SM/11361 | Anganwadi | Creating gravity based Provision Of Drinking water from spring water source for 38 Numbers of Anganwadi Centre in Mirik Block in the District of Darjeeling, under Neorakhola Water Supply & Maintenance Division, P.H.E Directorate, Kalimpong. |  | Junior Engineer III | ORD/000217/2022-2023 | 1111/NKWSMD | 05/08/2022 | 01/02/2023 | KAMAKHYA CONSTRUCTION | 97.78 | 97.88 | 100.1 | 0
Total | [13 empty] | 97.78 | 97.88 | 100.1