## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Plungdung Health Centre under Jorebunglow-Sukhiapokhri Block (Part-A) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000206/2022-2023 | 980/NKWSMD | 12/07/2022 | 11/08/2022 | KIRAN NIROLA | 3.85 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Pulungdung Health Centre under Jorebunglow-Sukhiapokhri Block (Part-B) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000209/2022-2023 | 983/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA ENTERPRISES | 2.53 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Simana Sub- Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola Water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000197/2022-2023 | 971/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA ENTERPRISES | 2.53 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Chamong-Health Centre and Nagari Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000208/2022-2023 | 982/NKWSMD | 12/07/2022 | 11/08/2022 | KIRAN NIROLA | 4.8 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Rangbhang Tarsing Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000205/2022-2023 | 979/NKWSMD | 12/07/2022 | 11/08/2022 | NAVRATNA CONSTRUCTION CO | 1.87 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Dara Gaon Primary Health Centre under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000207/2022-2023 | 981/NKWSMD | 12/07/2022 | 11/08/2022 | KIRAN NIROLA | 3.85 | 0 | 0 | 0
7 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 12 Nos of health Centre under Jorebunglow- Sukhiapokhri Block, in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11365 | Health Center | Creating gravity based Provision Of Drinking water from spring water source for Dooteria Kallej Valley Health Centre & Rangbull Health Centre under Jorebunglow-Sukhiapokhri in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000204/2022-2023 | 978/NKWSMD | 12/07/2022 | 11/08/2022 | NAVRATNA CONSTRUCTION CO | 4.26 | 0 | 0 | 100
Total | [13 empty] | 23.69 | 0 | 0