## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -I, under Jorebunglow-Sukhiapokhri Block (Part-I ) in the District of Darjeeling Under Neorakhola Water Supply & Mnt.Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000199/2022-2023 | 973/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA ENTERPRISES | 4.84 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Plungdung Gram Panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, under Neorakhola Water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000198/2022-2023 | 972/NKWSMD | 12/07/2022 | 11/08/2022 | KAMAKHYA ENTERPRISES | 4.12 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -II, under Jorebunglow-Sukhiapokhri Block (Part-II) in the District of Darjeeling Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000200/2022-2023 | 974/NKWSMD | 12/07/2022 | 11/08/2022 | MS EKTA CONSTRUCTION AND CO | 3.19 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision of Drinking water from spring water source for Paragari Tumsong Gram Panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000201/2022-2023 | 975/NKWSMD | 12/07/2022 | 11/08/2022 | MS EKTA CONSTRUCTION AND CO | 2.53 | 0 | 0 | 0
5 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -III, under Jorebunglow-Sukhiapokhri Block (Part-3) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000202/2022-2023 | 976/NKWSMD | 12/07/2022 | 11/08/2022 | MS EKTA CONSTRUCTION AND CO | 4.79 | 0 | 0 | 0
6 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Creating gravity based provision of drinking water from spring water source for 6 Nos of Gram panchayat, under Jorebunglow-Sukhiapokhri Block in the District of Darjeeling under Neorakhola water supply Division, PHE Directorate kalimpong | SM/11366 | Govt. Institutional Building (GP Building, Community Centre, Community Toilet, Other Govt. Offices) | Creating gravity based Provision Of Drinking water from spring water source for Pokhriabong Gram Panchayat -III, under Jorebunglow-Sukhiapokhri Block (Part-3) in the District of Darjeeling, Under Neorakhola water Supply & Mnt. Division, P.H.E. Directorate, Kalimpong. | Assistant Engineer II | Junior Engineer IV | ORD/000203/2022-2023 | 977/NKWSMD | 12/07/2022 | 11/08/2022 | NAVRATNA CONSTRUCTION CO | 4.12 | 0 | 0 | 0
Total | [13 empty] | 23.59 | 0 | 0