## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Augmentation of source for lower Takbia | SM/11374 | Augmentation | Continuation Engagement of 02 (Two) numbers Computer Operator (Graduate with Certificate in Computer Application) for the works related to Jal Jeevan Mission /Jal Swapno at the Office of the Executive Engineer, Neorakhola Water Supply & Maintenance Division, Public Health Engineering Directorate, Kalimpong for 01.09.2024 to 31.10.2024. | Assistant Engineer II | Junior Engineer I | ORD/000105/2024-2025 | 1551/NKWSMD | 30/08/2024 | 30/10/2024 | YAMA CONSTRUCTIONS LLP | 0.79 | 0 | 0 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Augmentation of source for lower Takbia | SM/11374 | Augmentation | Augmentation of source for lower takbia under Jal Swapno Programme for Goke-1, Block-Bijanbari-Pullbazar TSM No. 009479 |  |  | ORD/000126/2022-2023 | 806/NKWSMD | 30/06/2022 | 29/08/2022 | SAILESH RAI | 23.93 | 0 | 0 | 65
Total | [13 empty] | 24.72 | 0 | 0