## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) | SM/11378 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000118/2022-2023 | 1895/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 1.4 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) | SM/11378 | Retrofitting | Providing Functional Household Tap Connection by Strengthening mainline under Jal Jeevan Mission and Jal Swapno Programme for P.W.S Scheme at Sukhia Bazar, G.P - Sukhia Simana, Block - Jorebungalow Sukhia. |  |  | ORD/000162/2022-2023 | 938/NKWSMD | 12/07/2022 | 10/09/2022 | KAMAKHYA ENTERPRISES | 33.83 | 26.35 | 77.9 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection by strengthening mainline for PWS scheme at Sukhia Pokhri Bajar ( Mandir Line) | SM/11378 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000177/2022-2023 | 2577/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.4 | 0 | 0 | 0
Total | [13 empty] | 36.64 | 26.35 | 71.92