## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | SM/11381 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000131/2022-2023 | 1907/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 3.2 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | SM/11381 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Pokhriabong Turzum Panchyat - Pokhriabong-II Block - Jorebungalow Sukhia. |  |  | ORD/000169/2022-2023 | 945/NKWSMD | 12/07/2022 | 10/09/2022 | MOHAN MUKHIA | 67.07 | 47.24 | 70.43 | 100
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | SM/11381 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000191/2022-2023 | 2617/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 3.2 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing household tap connection under Jal Jeewan Mission / Jal swapno Programme from PWSS at Pokhriabong Turzum Tea Garden | SM/11381 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 1363/NKWSMD | 21/09/2022 | 21/09/2022 | Resource Division | 3.2 | 0 | 0 | 0
Total | [13 empty] | 76.68 | 47.24 | 61.6