## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar | SM/11382 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000102/2022-2023 | 1911/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 1.54 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap connection under Jal Jeewan Mission / Jal swapno Programme from existing PWSS at Maneybhang Bazar | SM/11382 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Manebhanjyang Bazar, Panchyat - Sukhia Simana Block - Jorebungalow Sukhia. |  |  | ORD/000170/2022-2023 | 946/NKWSMD | 12/07/2022 | 10/09/2022 | MOHAN MUKHIA | 48.83 | 46.89 | 96.01 | 0
Total | [13 empty] | 50.37 | 46.89 | 93.08