## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II | SM/11383 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000129/2022-2023 | 1905/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 1.94 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II | SM/11383 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Relling-I & II, GP - Rungli, Block - Bijanbari Pullbazar |  |  | ORD/000229/2022-2023 | 1443/NKWSMD | 28/09/2022 | 27/11/2022 | SUMAN PRADHAN | 60.32 | 0 | 0 | 100
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under JJM / JSP from existing PWSS at Relling _ I & II | SM/11383 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000189/2022-2023 | 2589/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 1.94 | 0 | 0 | 0
Total | [13 empty] | 64.2 | 0 | 0