## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | SM/11386 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000128/2022-2023 | 1904/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 2.92 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | SM/11386 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000188/2022-2023 | 2616/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 2.92 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | SM/11386 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 1364/NKWSMD | 21/09/2022 | 21/09/2022 | Resource Division | 2.92 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission/Jal Swapno Programme for balance household at Sumbuck & Kankaibong. | SM/11386 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme for balance household at Sumbuck & Kankeybong, GP - Jhepi, Block - Bijanbari Pulbazar. |  |  | ORD/000175/2022-2023 | 951/NKWSMD | 12/07/2022 | 08/01/2023 | SACHIN PRADHAN | 114.36 | 0 | 0 | 100
Total | [13 empty] | 123.12 | 0 | 0