## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | SM/11387 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at 6th Mile Bazar Gram GP - Rampuria & Mineral Spring, Block - Pull Bijanbari |  |  | ORD/000171/2022-2023 | 947/NKWSMD | 12/07/2022 | 10/09/2022 | PUSHKAR GURUNG | 29.98 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | SM/11387 | Retrofitting | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  |  | BILL/00078/2023-2024 | BP-2023-24-40 | 11/05/2023 | 11/05/2023 | KASHYAP COMPUTERS | 0.34 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | SM/11387 | Retrofitting | computer operator payment |  |  | BILL/00484/2023-2024 | BP-2023-24-193 | 30/09/2023 | 30/09/2023 | KASHYAP COMPUTERS | 0.51 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household household tap connection by strengthening mainline for PWS scheme at 6th Mile Bazaar. under Jal Jeewan Mission/Jal Swapno Programme. | SM/11387 | Retrofitting | Acceptance order for Engagement of DEO(Data Entry Operator) through agency/contractor for office of the Executive Engineer, Kurseong Divisaion, PHED, for Operation proper e-Governance activity i.e. JJM at kurseong under kurseong Division PHE Dte. |  |  | BILL/00011/2023-2024 |  | 18/04/2023 | 18/04/2023 | KASHYAP COMPUTERS | 0.85 | 0 | 0 | 0
Total | [13 empty] | 31.68 | 0 | 0