## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | SM/11389 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000132/2022-2023 | 1908/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 0.39 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | SM/11389 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Bijuwa Gaon Pulundung GP - Pulundung, Block - Jorebungalow Sukhia |  |  | ORD/000163/2022-2023 | 939/NKWSMD | 12/07/2022 | 10/09/2022 | KIRAN NIROLA | 12.21 | 12.09 | 99 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | SM/11389 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000194/2022-2023 | 2591/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 0.39 | 0 | 0 | 0
4 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing functional household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing PWSS at Bijuwa goan, Pulungdung | SM/11389 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1267/NKWSMD | 05/09/2022 | 05/09/2022 | Resource Division | 0.39 | 0 | 0 | 0
Total | [13 empty] | 13.37 | 12.09 | 90.39