## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar | SM/11392 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Takdah Bazar GP - Takdah Block - Rungli Rungliot. |  |  | ORD/000174/2022-2023 | 950/NKWSMD | 12/07/2022 | 22/03/2023 | NAVRATNA CONSTRUCTION CO | 150.61 | 106.56 | 70.75 | 100
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar | SM/11392 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 1910/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 5.85 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household tap connection under Jal Jeewan Mission / Jal Swapno Programme from existing scheme at Takdah Bazar | SM/11392 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000192/2022-2023 | 2618/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 5.85 | 0 | 0 | 0
Total | [13 empty] | 162.31 | 106.56 | 65.65