## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam | SM/11393 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for Piped Water Supply Scheme at Glenburn Singritam, Gram Panchayat - Singritam, Block - Rangli Rangliot. |  |  | ORD/000087/2023-2024 | 686/NKWSMD | 12/07/2023 | 06/04/2024 | PUSHKAR GURUNG | 166.03 | 63.07 | 37.98 | 92
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme from existing scheme at Glenburn & Singritam | SM/11393 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000078/2023-2024 | 766/NKWSMD | 19/07/2023 | 19/07/2023 | Resource Division | 8.61 | 0 | 0 | 0
Total | [13 empty] | 174.64 | 63.07 | 36.11