## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. | SM/11394 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000133/2022-2023 | 1909/NKWSMD | 15/12/2022 | 15/12/2022 | Resource Division | 8.41 | 0 | 0 | 0
2 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. | SM/11394 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000197/2022-2023 | 2593/NKWSMD | 17/02/2023 | 17/02/2023 | Resource Division | 8.41 | 0 | 0 | 0
3 | DARJEELING |  | Neorakhola W/S & Mtc.Div. | Providing Functional Household Tap Connection under Jal Jeewan Mission/Jal Swapno Programme form existing scheme at Teesta Valley Tea Garden. | SM/11394 | Retrofitting | Providing Functional Household Tap Connection under Jal Jeevan Mission and Jal Swapno Programme for PWS Scheme at Teesta Valley, GP - Rungli, Block - Rungli Rungliot. |  |  | ORD/000176/2022-2023 | 952/NKWSMD | 12/07/2022 | 30/04/2024 | NAVRATNA CONSTRUCTION CO | 167.77 | 0 | 0 | 92
Total | [13 empty] | 184.59 | 0 | 0